## Sheet1
Motor Garden Bazzana
Project Start: 6 October 2025 |  |  |  |  | Month | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun
Gantt v1.0.0 |  |  |  |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
[5 empty] | Days | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | Weeks # | Hours # | Cost €
TASK | ASSIGNED | % | START | END
Intro
define goals | Baldassarri Bruno | 100% | 2025-10-06 | 2025-10-31 |  | 1 | [34 empty] | 3 | 0 | 0
Conduct studies | Bugada Giovanni | 50% | 2025-10-10 | 2025-10-31 | [36 empty] | 3 | 0 | 0
estabilish comms | Bugada Giovanni | 10% | 2025-10-15 | 2025-10-31 | [36 empty] | 2 | 0 | 0
set up team | Both | 5% | 2025-10-25 | 2025-10-31 | [36 empty] | 0 | 0 | 0
Development | [40 empty] | 0 | 0 | 0
Execute tasks | Both | 70% | 2025-10-15 | 2025-12-31 | [36 empty] | 11 | 0 | 0
Monitor progress | Baldassarri Bruno | 80% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Manage resources | Both | 50% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Provide updates | Both | 90% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Marketing | [40 empty] | 0 | 0 | 0
Define target audience and buyer personas | Bugada Giovanni | 20% | 2025-10-15 | 2025-12-31 | [36 empty] | 11 | 0 | 0
Develop social media strategy | Bugada Giovanni | 20% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Track and analyze performance metrics | Baldassarri Bruno | 10% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Set up email marketing campaign | Both | 5% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Selling | [40 empty] | 0 | 0 | 0
Define sales strategy and goals | Bugada Giovanni | 60% | 2025-10-15 | 2025-12-31 | [36 empty] | 11 | 0 | 0
Develop pricing model | Baldassarri Bruno | 30% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Identify and reach out to potential clients | Bugada Giovanni | 20% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Monitor sales performance | Baldassarri Bruno | 10% | 2025-11-01 | 2025-12-31 | [36 empty] | 8 | 0 | 0
Componenti: | Baldassarri Bruno | [39 empty] | 113 | 0 | 0
Bugada Giovanni
Hours x Week: |  | h
Costo Risorse Interne: |  | €/h
Costo Risorse Esterne: |  | €/h